COMP 202 – Software Engineering

Spring 2026

LaserZone

Online Reservation System

Initial Work Plan — Post Kick-off Submission

Team Members: Mustafa Göçmen  •  Tuna Öcal  •  Muhammet Gümüş  •  Begüm Rana Türkoğlu  •  Eylül Sena Altunsaray

Date: March 2026

# 1. Project Overview

LaserZone is a web-based reservation system developed for a laser tag business. Customers can register, browse available time slots, and make reservations online. A key feature is the Group Matchmaking system, which allows a group leader to open a reservation for a partial group and let other users send join requests — filling up the session collaboratively. All payments are handled on-site at the venue; the platform manages reservations only.

Technology Stack:

- Frontend: React.js, TailwindCSS

- Backend: Node.js + Express (REST API)

- Database: MySQL

- Authentication: JWT (JSON Web Tokens)

- E-mail: SendGrid / SMTP

- Version Control: GitHub

- Project Management: Jira / Trello (Agile Board)

# 2. Group Matchmaking Feature

The Group Matchmaking feature allows a group that does not have enough players to fill a session (e.g. 7 out of 10) to open their reservation publicly so that other users can request to join. The group leader has full control over who gets approved. Payment is always handled at the venue — no online payment is involved.

| Step | Action | Details |
| --- | --- | --- |
| 1 | Group leader creates reservation | Selects date, time, total capacity (e.g. 10 players), enters current party size (e.g. 7). Marks as 'Open Group'. |
| 2 | System lists the open group | Other users see the open group in the 'Find a Group' page with details: time, slots left (3/10), leader info. |
| 3 | User sends a join request | User specifies how many people they bring (e.g. 2). Request is sent to the group leader. No payment on the platform. |
| 4 | Group leader reviews requests | Leader sees pending requests in their dashboard. Can approve or reject each request individually. |
| 5 | Group is filled / locked | When total reaches the max capacity (10/10), the reservation is automatically locked. All members receive a notification. |
| 6 | Payment at venue | Each player pays their share at the laser tag venue on arrival. The system handles only the reservation, not payments. |

## Group Leader Dashboard

When a group leader logs in, their dashboard shows:

- Current group status: e.g. 7 / 10 players confirmed

- List of pending join requests with requester name and party size

- Approve / Reject buttons for each request

- Option to close the group early (lock reservation before full capacity)

- Option to cancel the entire reservation

## Edge Cases & Business Rules

- If total approved players exceed max capacity, further requests are automatically rejected

- If the group is not filled 2 hours before the session, the leader is notified and can decide to proceed or cancel

- A join request can only be sent if the remaining slots are sufficient for the requester's party size

- Once the reservation is locked (full or manually closed), no more join requests are accepted

# 3. User Stories & Estimates

Total: 13 User Stories  |  Total: 97 Story Points across 4 Sprints

| ID | User Story | Priority | Est. (SP) | Sprint |
| --- | --- | --- | --- | --- |
| US-01 | As a customer, I want to register and log in to the system so that I can track my personal reservations. | High | 5 | Sprint 1 |
| US-02 | As a customer, I want to view available time slots and arenas so that I can choose a suitable slot. | High | 8 | Sprint 1 |
| US-03 | As a customer, I want to create a reservation (date, time, number of players) so that I can guarantee the arena in advance. | High | 8 | Sprint 1 |
| US-04 | As a group leader, I want to create an open-group reservation so that other users can join my group. | High | 8 | Sprint 1 |
| US-05 | As a customer, I want to browse open groups and send a join request (with my party size) so that I can fill up a group. | High | 5 | Sprint 1 |
| US-06 | As a group leader, I want to approve or reject incoming join requests so that I can control who plays with my group. | High | 5 | Sprint 2 |
| US-07 | As a customer, I want to cancel or modify my reservation so that I have flexibility when my plans change. | Medium | 5 | Sprint 2 |
| US-08 | As a customer, I want to receive an e-mail confirmation after my reservation so that I can save the details. | Medium | 3 | Sprint 2 |
| US-09 | As a customer, I want to view my reservation history so that I can track how often I have played. | Low | 3 | Sprint 3 |
| US-10 | As a business owner, I want to manage all reservations (view, approve, cancel) so that I can keep operations organized. | High | 8 | Sprint 2 |
| US-11 | As a business owner, I want to define working hours and available slots so that I can control the booking calendar. | High | 5 | Sprint 2 |
| US-12 | As a business owner, I want to view occupancy reports and statistics so that I can make informed business decisions. | Medium | 5 | Sprint 3 |
| US-13 | As a customer, I want to see real-time slot availability so that I can plan without worrying about overlaps. | Medium | 5 | Sprint 3 |

Note: 1 Story Point ≈ 3 hours of work. Estimates are based on a 5-member team capacity.

# 4. Task Breakdown

Each user story is decomposed into actionable tasks with individual estimates and assignees:

| US | Task ID | Task Description | Assignee | Est. | Sprint |
| --- | --- | --- | --- | --- | --- |
| US-01 | T-01 | Design user database schema | Backend Dev | 3h | Sprint 1 |
| US-01 | T-02 | Implement register/login API endpoints (JWT) | Backend Dev | 4h | Sprint 1 |
| US-01 | T-03 | Build register & login UI pages | Frontend Dev | 4h | Sprint 1 |
| US-01 | T-04 | Write authentication unit tests | QA / Dev | 2h | Sprint 1 |
| US-02 | T-05 | Implement availability query API | Backend Dev | 4h | Sprint 1 |
| US-02 | T-06 | Build calendar/slot display component | Frontend Dev | 6h | Sprint 1 |
| US-03 | T-07 | Design reservation database schema | Backend Dev | 3h | Sprint 1 |
| US-03 | T-08 | Implement reservation creation API (conflict check) | Backend Dev | 6h | Sprint 1 |
| US-03 | T-09 | Build reservation form UI | Frontend Dev | 5h | Sprint 1 |
| US-03 | T-10 | Write reservation integration tests | QA / Dev | 3h | Sprint 1 |
| US-04 | T-11 | Design group reservation DB schema (open/closed, party size) | Backend Dev | 3h | Sprint 1 |
| US-04 | T-12 | Implement open-group creation API | Backend Dev | 4h | Sprint 1 |
| US-04 | T-13 | Build open-group creation UI for group leader | Frontend Dev | 4h | Sprint 1 |
| US-05 | T-14 | Implement open groups listing API with filters | Backend Dev | 3h | Sprint 1 |
| US-05 | T-15 | Build open groups browse page & join request form | Frontend Dev | 5h | Sprint 1 |
| US-05 | T-16 | Implement join request submission API | Backend Dev | 3h | Sprint 1 |
| US-06 | T-17 | Build group leader dashboard (pending requests list) | Frontend Dev | 5h | Sprint 2 |
| US-06 | T-18 | Implement approve/reject join request API | Backend Dev | 4h | Sprint 2 |
| US-06 | T-19 | Auto-lock reservation when group is full | Backend Dev | 3h | Sprint 2 |
| US-06 | T-20 | Send notifications to all members on group full/approved | Backend Dev | 3h | Sprint 2 |
| US-07 | T-21 | Implement cancel & modify reservation API endpoints | Backend Dev | 4h | Sprint 2 |
| US-07 | T-22 | Build reservation management UI (customer side) | Frontend Dev | 4h | Sprint 2 |
| US-08 | T-23 | Integrate e-mail service (SendGrid/SMTP) | Backend Dev | 3h | Sprint 2 |
| US-08 | T-24 | Design e-mail confirmation templates | Frontend Dev | 2h | Sprint 2 |
| US-10 | T-25 | Build admin panel – reservation list & filters | Full-stack Dev | 6h | Sprint 2 |
| US-10 | T-26 | Implement admin approve/cancel operations | Backend Dev | 3h | Sprint 2 |
| US-11 | T-27 | Implement working hours & slot management API | Backend Dev | 4h | Sprint 2 |
| US-11 | T-28 | Build admin calendar configuration UI | Frontend Dev | 4h | Sprint 2 |
| US-09 | T-29 | Reservation history API & UI (customer) | Full-stack Dev | 4h | Sprint 3 |
| US-12 | T-30 | Occupancy reports & chart dashboard | Full-stack Dev | 6h | Sprint 3 |
| US-13 | T-31 | Real-time availability (WebSocket / polling) | Backend Dev | 5h | Sprint 3 |
| US-13 | T-32 | Live update UI integration | Frontend Dev | 4h | Sprint 3 |
| - | T-33 | Full system testing & bug fixes | All Team | 6h | Sprint 4 |
| - | T-34 | UI/UX final polish & responsive design | Frontend Dev | 4h | Sprint 4 |
| - | T-35 | Deployment & CI/CD setup | DevOps/Backend | 4h | Sprint 4 |
| - | T-36 | Final documentation & README | All Team | 3h | Sprint 4 |

# 5. Sprint Plan

| Sprint | Duration | Target US | Total SP | Deliverables |
| --- | --- | --- | --- | --- |
| Sprint 1 | 2 weeks | US-01 to US-05 | 39 SP | Auth, slot availability, standard reservation, open-group creation & join requests |
| Sprint 2 | 2 weeks | US-06, US-07, US-08, US-10, US-11 | 28 SP | Group leader approval flow, cancel/modify, e-mail notifications, admin panel, slot config |
| Sprint 3 | 2 weeks | US-09, US-12, US-13 | 13 SP | Reservation history, occupancy reports, real-time availability |
| Sprint 4 | 2 weeks | Tech Debt & Deployment | 17 SP | Full testing, UI polish, CI/CD deployment, final documentation |

## Sprint 1 Detail (Weeks 1–2)

Goal: Working app where a customer can register, browse slots, make a reservation, and either create or join an open group.

- Week 1: Database schemas, auth API, register/login UI, open-group DB design

- Week 2: Slot availability API, calendar UI, reservation form, open-group creation & browse pages, join request submission

- Demo: Customer can register, view slots, create a solo or open-group reservation, and send a join request to an existing open group

## Sprint 2 Detail (Weeks 3–4)

Goal: Group leader approval flow, reservation management for customers, e-mail notifications, and admin panel.

- Group leader can approve/reject join requests; reservation auto-locks when full

- Customers can cancel or modify reservations

- E-mail confirmations sent on reservation create, approval, and group full events

- Admin can view all reservations, configure working hours and slots

## Sprint 3 Detail (Weeks 5–6)

Goal: Advanced features — reservation history, occupancy dashboard, real-time availability.

## Sprint 4 Detail (Weeks 7–8)

Goal: Quality, deployment, and final demo readiness.

- Comprehensive testing, bug fixes, UI/UX polish

- CI/CD pipeline and production deployment

- Complete project documentation

# 6. Team Assignments

| Team Member | Role | Responsibilities | Tasks |
| --- | --- | --- | --- |
| Mustafa Göçmen | Full-stack Dev / Scrum Master | Backend API, Auth, Sprint coordination | T-02,04,08,10,12,18,19,20,29 |
| Tuna Öcal | Backend Developer | Backend APIs, e-mail service, group logic, deployment | T-05,14,16,21,23,31,33,35 |
| Muhammet Gümüş | Frontend Developer | UI pages, components, admin panel, responsive design | T-03,06,09,13,15,17,22,24,25,28,34 |
| Begüm Rana Türkoğlu | Database Designer | DB schema design, table relations, query optimization, seed data | T-01,07,11,27,30 |
| Eylül Sena Altunsaray | Database Designer / Docs | DB schema design, migrations, integration tests, documentation | T-07,11,26,32,36 |

# 7. Initial Velocity

| Metric | Value |
| --- | --- |
| Team Size | 5 members |
| Sprint Duration | 2 weeks (10 working days) |
| Working Hours per Person per Day | 3–4 hours (student schedule) |
| Total Person-Hours per Sprint | ~150 hours (5 members × 10 days × 3 hrs) |
| 1 Story Point Equals | ~3 hours of work |
| Initial Velocity | 18–21 SP / Sprint |
| Total Project Story Points | 97 SP across 4 Sprints |

Velocity Calculation:

- Capacity per sprint: 5 members × 10 days × 3 hours = 150 person-hours

- 1 Story Point = ~3 hours (development + testing)

- Initial velocity = 150 ÷ 3 × 0.40 buffer = ~20 SP/sprint

- Velocity will be recalculated after each sprint retrospective

# 8. Risks & Mitigation

- Risk: Time constraints due to other courses → Mitigation: Weekly stand-ups, strict priority ordering

- Risk: Real-time features more complex than estimated → Mitigation: Start with polling in Sprint 3; WebSocket is optional enhancement

- Risk: Group matchmaking edge cases (race conditions on join requests) → Mitigation: Server-side locking, thorough integration tests in Sprint 2

- Risk: Database schema changes mid-project → Mitigation: Schema review meeting in Sprint 1 before coding begins

# 9. Definition of Done (DoD)

A user story is considered Done when ALL of the following criteria are met:

- Code is pushed to GitHub and reviewed by at least one other team member

- Unit tests are written and passing

- Integration test is completed

- Feature is demonstrated as working software to the customer

- Task board is updated (tasks moved to Done column)

- No critical bugs; any known issues are documented

COMP 202 Spring 2026  •  LaserZone Reservation System  •  Initial Work Plan